## ok can we make above data in RA
Type/Category | Success Criteria | Description | Responsible | Accountable | Consulted | Informed
Deployment | The SPA is containerized and runs without errors within the ECS Fargate environment. | The SPA is packaged into a container image that is deployed to and runs without errors on the ECS Fargate platform. | DevOps | DevOps | Development, QA, Security | Development, QA, Security, Stakeholders
Networking | The application is accessible via an Application Load Balance (ALB) or other specified means. | The SPA is accessible to users via an ALB or other load balancing mechanism. | DevOps | DevOps | Development, QA, Security | Development, QA, Security, Stakeholders
CI/CD | The deployment process is automated through the CI/CD pipeline. | The process of building, testing, and deploying the SPA is automated using a CI/CD pipeline. | DevOps | DevOps | Development, QA, Security | Development, QA, Security, Stakeholders
Testing | Integration testing is completed without critical issues. | The SPA is integrated with its dependent services and tested to ensure that it functions as expected. Any critical issues identified during integration testing are addressed and resolved. | QA | QA | Development, Security | Development, Security, Stakeholders
Integration | The SPA successf interacts with dependent services (e.g., databases) as expected. | The SPA is able to successfully communicate with and interact with its dependent services. | Development | Development | QA, Security | QA, Security, Stakeholders
Testing | Performance testing is completed, and the application meets specified performance criteria (e.g., response times, throughput) under various load scenarios. | The SPA is subjected to performance testing to ensure that it meets the specified performance criteria under various load scenarios. Any performance bottlenecks or issues identified during testing are addressed and improved. | QA | QA | Development, Security | Development, Security, Stakeholders
Security | AWS IAM roles and permissions are configured correctly for the ECS servi Security groups and network configurations are properly set up to restrict access as required. - Vulnerability scans and security audits do not reveal critical security issues. | The ECS service is configured with the correct AWS IAM roles and permissions. The security groups and network configurations are properly set up to restrict access to the ECS service as required. Vulnerability scans and security audits are performed on the ECS service and no critical security issues are identified. | Security | Security | Development, QA, DevOps | Development, QA, DevOps, Stakeholders
CI/CD | Automated resource cleanup at the end of the CI/CD pipeline is successfu No lingering or unused resources result in unexpected costs. | The CI/CD pipeline includes a step to clean up any resources that are no longer needed after the SPA has been deployed. This ensures that no lingering or unused resources result in unexpected costs. | DevOps | DevOps | Development, QA, Security | Development, QA, Security, Stakeholders